**Notes– Simulation Project Meeting – 09.09.21**

|  |  |
| --- | --- |
| Date: |  |
| Meeting details: | MS Teams |
| Attendees: | Jennifer Minford (Notes)  Wai Tse (Chair)  James Clark  Thomas Jerrom  Beccie Williams Locke |
| Apologies: | Tim Mason  Rozz McDonald  Emily Foote  Gio Edwards  Timothy Spencer  Sarah Woods  Rob Lutyens  Dan Freshwater-Turner (Chair)  Liz Berragan  Lisa Merrett  No response  Jennifer Coombs  Anna Stevenson  Alison Potter  Becky Thomas  Curtis Whittle  Liz Tooby  Maria Smith  Oliver Colbourne-Laight  Kate Thomson  Caroline Lacy  Natalie Kewley  Sam Kirkwood  Julian Wright  Anya Makin-Terry  Maria Tsakmakis  Adrian Humphry  Leigh Beard  Alex Aquilina |
|  |  |

|  |
| --- |
| **Welcome and Introductions** – WT – small group today due to clinical pressures.  **Project Updates**:  **James Clark** – Awarded 30k 18 months ago. Fellow employed to support program – AI/video analytics in learning complex surgery. 4 x presentations completed and paper in press.  Hospital has now financially signed into the project – have recruited a MSC student – completed own studies with distinction. MSC work slightly off HEE funding brief – “predicted modelled score for laparoscopic surgery” – scores skill of surgeon through first 5 minutes of operation to predict length of surgery – specifically for gallbladder operation, varying in time due to difficulty. Research assists with operational theatre scheduling/staff allocations. Very positive outcomes of funding.  Fellow validated AI for training purposes – meets original brief for HEE funding.  Sustainability-Clinical fellow approved for next year – Trust supports as benefits witnessed – demonstrates innovation.  Fellows also act as locums – benefits Trust staffing.  Final report pending and have submitted to October showcase event.  **Thomas Jerrom** – HEE funded Sim Fellow stepped back from program to cover nursing secondment (maternity leave) – not currently primary sim fellow – replacement employed – fellow/ECMO lead on point with SIM matters. Following maternity cover, original fellow return to assist during final funding period. Intention is to have 2 x SIM Fellows part time for 1 year; 2 x alternate cover for 2 years achieved instead – some overlap in cover.  Part-task trainer sessions ongoing - limited due to COVID  Next ECMO course October 2021 – relaxation of COVID rules resulting in more SIM activities.  Canulation Simulation planned – 15-20 persons not possible due to covid – plans underway now with restrictions lifting.  Equipment shortages – ECMO components lacking – emergencies with minimum equipment addressed as a result – useful byproduct of Pandemic – latent threats and protocols will be topic for Event Showcase in October (poster submitted).  Future of projects - Number of funded nurse posts in PICU, support for ECMO program secured – fall back if Sim Fellow post not funded.  WT – we’d like to have reports/presentations on website so others can see the positive impact of HEE Sim funded projects. Please sent presentation, we can send out with minutes.  JC – recurrent funding would be excellent.  WT – you will need to enter another application.  WT – see you at the next Network meeting on 7th October. |

Next Simulation Network Meeting:

6th December 2021 - MS Teams